## High Lvl Sched
Project
Department
Date: 4/20/22
| 2015 | [21 empty] | 2016
| August |  |  |  |  | September |  |  |  | October |  |  |  | November |  |  |  |  | December |  |  |  | January |  |  |  | February |  |  |  |  | March
Location or Item | 3 | 10 | 17 | 24 | 31 | 7 | 14 | 21 | 28 | 5 | 12 | 19 | 26 | 2 | 9 | 16 | 23 | 30 | 7 | 14 | 21 | 28 | 4 | 11 | 18 | 25 | 1 | 8 | 15 | 22 | 29 | 7 | 14 | 21 | 28
Planning/Design
Planning Fund Approval | bar: August 24 to September 7
Design Team Proposal | bar: September 7
Program - Schematic Design | October 5: sign-off; October 12: sign-off
Design Development | October 19: sign-off
Construction Documents | November 2: sign-off
Bidding Process | November 23: sign-off
50% Document Review
Misc Equipment Review & Schedule
Tel/Data Review
Scope Review with Facilties & EHS
90% Drawiing Review w/ Department
Keying Review with Department
Incorporation of Department Changes
Confirm Bidding docs included in Spec
Establish Bid List
Construction | February 15: sign-off
BiddingTimeframe
Pre-Bid Meeting
Issuance of Addenda for Clarifications
Bid Opening
GC Selection Process
Receipt of Liability Insurnace
Innitiation of Contract
Move-in
Pre-construction Meeting
Construction
Move #6
Move Review Process
Punch List Inspection
Equipment Confirmation
Department Walk- thru
Punch List Inspection
Activation of Phone Lines
Certificate of Substantial Completion
Department Occupancy/Relocation
Post Occupancy
Assembly of O&M's & Record Dwgs
Turn over O&M's *& Dwgs to FMD
Project Close Out

## Sheet1
Preliminary Project Schedule
Project 11041
Department | Orthopaedics and Internal Medicine
Date:
|  | 2010 | [16 empty] | 2011 | [51 empty] | 2012
|  | September |  |  |  | October |  |  |  | November |  |  |  |  | December |  |  |  |  | January |  |  |  | February |  |  |  | March |  |  |  |  | April |  |  | May |  |  |  |  | June |  |  |  | July |  |  |  | August |  |  |  |  | September |  |  |  | October |  |  |  |  | November |  |  |  | December |  |  |  |  | January |  |  |  | February |  |  |  | March |  |  |  | April |  |  |  |  | May |  |  |  | June |  |  |  | July |  |  |  |  | August |  |  |  | September |  |  |  | October |  |  |  |  | November |  |  |  | December
Location or Item |  | 6 | 13 | 20 | 27 | 4 | 11 | 18 | 25 | 1 | 8 | 15 | 22 | 29 | 5 | 12 | 19 | 26 | 3 | 10 | 17 | 24 | 31 | 7 | 14 | 21 | 28 | 7 | 14 | 21 | 28 | 4 | 11 | 18 | 25 | 2 | 9 | 16 | 23 | 30 | 5 | 12 | 19 | 26 | 4 | 11 | 18 | 25 | 1 | 8 | 15 | 22 | 29 | 5 | 12 | 19 | 26 | 3 | 10 | 17 | 24 | 31 | 7 | 14 | 21 | 28 | 5 | 12 | 19 | 26 | 2 | 9 | 16 | 23 | 30 | 6 | 13 | 20 | 27 | 5 | 12 | 19 | 26 | 2 | 9 | 16 | 23 | 30 | 7 | 14 | 21 | 28 | 4 | 11 | 18 | 25 | 2 | 9 | 16 | 23 | 30 | 6 | 13 | 20 | 27 | 3 | 10 | 17 | 24 | 1 | 8 | 15 | 22 | 29 | 5 | 12 | 19 | 26 | 3 | 10 | 17 | 24 | 31
Planning/Design
PIF Review with Department
Establish Preliminary Scope/Budget
Receive Budget Approval
A/E Selection
Construction Documents
Schematic Design
Design Development
50% Document Review
Misc Equipment Review & Schedule
Tel/Data Review
Scope Review with Facilties & EHS
90% Drawiing Review w/ Department
Keying Review with Department
Incorporation of Department Changes
Confirm Bidding docs included in Spec
Establish Bid List
Bidding Process
BiddingTimeframe
Pre-Bid Meeting
Issuance of Addenda for Clarifications
Bid Opening
GC Selection Process
Receipt of Liability Insurnace
Innitiation of Contract
Construction
Pre-construction Meeting
Construction
Move #6
Move Review Process
Punch List Inspection
Equipment Confirmation
Department Walk- thru
Punch List Inspection
Activation of Phone Lines
Certificate of Substantial Completion
Department Occupancy/Relocation
Post Occupancy
Assembly of O&M's & Record Dwgs
Turn over O&M's *& Dwgs to FMD
Project Close Out