## Checklist Project Manager
Project Manager Project Closeout Checklist
Project Number
Project Name
Planner / PM
Close Out Items
Scheduled 1 year warranty walk through. Please provide date scheduled. Date: ______________________________
Confirmed that Facilities Operations and/or Users have received equipment training. Systems include but are not limited to MEPFP, Fire Alarm, Building Automation, Building Access, Lighting Controls, and A/V.
Confirmed that all attic stock required by the specifications has been received and stored in an agreeable location with Facilities Operations.
Received, filed, and distributed the Test, Adjust, and Balance Report and the Final Commissioning Report.
Confirmed all warranties are included in the O&Ms. Confirmed receipt of O&Ms and electronically filed Operations and Maintenance Manuals and saved in the Archive file and notified Facilities and both saved in the project file.
Notified the Planning Analyst of lab renovation project completion to facilitate updates to the lab quality rating.
Completed the Space Utilization Form and forwarded the form to the space management team. Requested the architect forward PDF and CAD Plans to the space management team.
Received PDF and CAD final Record Drawings (As-Builts) filed in the Project File and forwarded to space management team.
Confirmed that all change orders have been issued for all contracts and purchase orders.
The CSC has been established, fully executed and filed. Substantial Completion Date: _______________________
Bid documents/construction documents (PDF & CAD) are in the project files.
Project Manager Signature /Approval Signature: _________________________________
rev. 01/22/24
Yes
N/A
N/A
Yes
N/A
Yes
N/A
Yes
N/A
Yes
N/A
Yes
N/A
Yes
N/A
Yes
N/A
Yes
Yes
Yes
No Drawings Required
Yes
N/A