## Sheet1
Project Communication Plan - EXAMPLE
| Communication | Method | Frequency | Goal | Sender | Recipient
| Project Charter | Email | Preliminary Funding Request | First introduction to the document; review project information for omissions or required corrections; discuss the communication plan with the project team | Project Planner | Planning & Projects Team
|  |  | Full Funding Request |  |  | Key Stakeholders
|  |  | When project scope, budget, funding, or key project members change |  |  | Integrated Campus Planning & Operational Services
| Project Progress Update | Email | Monthly, 1st Friday | Informational: review project status | Project Manager | Planning & Projects Team
Key Stakeholders
| Bi-Weekly Project Meeting | Meeting | Bi-Weekly, Wednesday (standing meeting) | Review current project status, schedule, ongoing tasks, and responsible team members | Project Manager | Planning & Projects Team
Project Consultants
| Current Projects | Planning & Projects Website | Quarterly | Provide a project overview and current status, share team members, recent renderings or photos, etc. | Communications Manager | Campus-wide community
External
| Approved Scope Change Notification | Email | As needed | Present the change order to the client (department funded) and gain approval | Project Manager | Planning & Projects Team
Key Stakeholders
Project Consultants and Contractors
Communication: The communication topic and content.
Method: The vehicle used to communicate.
Frequency: The occurrence and schedule of the communication.
Goal: The purpose and desired outcome.
Sender: The person responsible for initiating the communication.
Recipient: The people receiving the communication.