## Sheet1
RESPONSIBILITY KEY
BM = Business Manager
DH = Department Head
EHS = Environmental Health and Safety Personnel
FMD = Facilities Management Department
LC = Lab Contact
PI = Principal Investigator
RS = Radiation Safety
Responsible Party | Laboratory Closure Checklist | Date Completed | Signature
BM | Meet with PI and Lab Contact to discuss lab closure
DH/BM | Send email to rentforspace@wustl.edu to indicate desire to vacate. Include room numbers for all rooms to be returned
BM | BM to identify those rooms which are laboratory related and to be decommissioned by EHS and RS
BM | Setup a timeline with Lab contact for lab closure
BM/PI/LC | Notify EHS of impending lab closure. Include room numbers of all rooms to be returned
BM/PI/LC | Notify Radiation Safety of impending lab closure. Include room numbers of all rooms to be returned
PI/LC | Determine chemicals/equipment/supplies/furniture to be donated to other labs, divisions or departments at WU and begin removal from lab space.
PI/LC | Submit Requests for Pickup of (1) unwanted chemicals, (2) regulated equipment, "Universal" waste, and hazardous materials, (3) biohazard and sharps materials, and (4) radioactive waste to EHS and Radiation Safety at least 4-6 weeks in advance of desired lab closure date. Refer to the information checklists/documents on the EHS and Radiation Safety websites, http://ehs.wustl.edu/hmm/Pages/default.aspx and https://radsafety.wustl.edu/An1Pages/An1-Radwaste.htm.
PI/LC | Radioactive materials transferred or disposed of through Radiation Safety. Lab Contact brings Radioactive waste to Radiation Safety staff and vehicle with proper paperwork, per Radiation Safety guidance.
PI/LC | Final visual survey and radioactive material wipe tests of lab and common areas by lab staff
PI/LC | All radioactive waste and material must be out of room prior to Radiation Safety performing closeout surveys. When done, Radiation Safety will do a preliminary walk-thru to decommission any room or hood displaying the radiation symbol. Do not move any equipment with the symbol unless it displays a dated sign stating it has been decommissioned.
PI/LC | Remove all unwanted, non-hazardous and non-regulated waste and debris. Large trash disposal carts are available by calling Facilities at 362-3100. Glass, electrical parts/cords, equipment, and furniture cannot be put into trash carts or waste cans. Refer to the information checklists/documents on the EHS, Radiation Safety and FMD websites.
PI/LC | Glass waste must be properly packaged for trash collection. Refer to the information checklists/documents on the EHS and Radiation Safety websites.
PI/LC | Gas cylinders returned to vendor
PI/LC | Fume hood cleared of all materials
PI/LC | Lab benches, desks, storage cabinets, drawers cleared of all materials and cleaned of hazardous and unknown residues.
PI/LC | Shared rooms (cold rooms, warm rooms, tissue culture rooms, equipment rooms) must be cleared of all materials that belong to the lab being decommissioned and surfaces disinfected and cleaned. Indicate with signage which portion of a shared room has been cleaned/disinfected/closed out and which portions belong to active laboratory operations and who is responsible for those operations.
PI/LC | Interiors of chemical fume hoods have been washed with a suitable cleaner and/or disinfectant, and wiped-down. Post a dated sign on the hood saying it is clean.
LC | Final visual survey and wipe tests of lab and common areas by lab staff.
PI/LC | Biosafety Cabinets have been gas de-contaminated by ACE or other vendor. Vendor to post a dated sign on the BSC indicating it is clean.
BM/PI/LC | All non-regulated (non-EHS) lab equipment and supplies must be removed. If there is any warning signage still in place in the lab or on the door, personnel moving furniture must receive brief hazard communication training. You may contact Dave William of Facilities – williamsd@wusm.wustl.edu to assist finding a removal contractor.
BM/PI/LC | All furniture must be removed. If there is any warning signage still in place in the lab or on the door, personnel moving furniture must receive brief hazard communication training. The BM/PI/LC may contact other areas within WU to dispose of furniture, or contact Tina Long of Facilities – longt@wusm.wustl.edu to survey the furniture for reuse or disposal
EHS | Hazardous and/or unwanted chemical waste removed, assuming adequate advance warning has been provided (4 to 6 weeks), otherwise EHS will assist department in hiring an approved outside vendor to remove hazardous materials at department's expense, or EHS will bill department at overtime rates for time and expenses to remove the material. It may take 4 to 6 weeks before EHS has staff resources to complete this operation and laboratory must remain locked, posted and the department's possession during that time.
EHS | Biohazard and sharps waste removed, assuming adequate advance warning has been provided (4 to 6 weeks), otherwise EHS will assist department in hiring an approved outside vendor to remove hazardous materials at department's expense, or EHS will bill department at overtime rates for time and expenses to remove the material. It may take 4 to 6 weeks before EHS has staff resources to complete this operation and laboratory must remain locked, posted and the department's possession during that time.
RS | Department will be billed for time and materials if Radiation Safety needs to decontaminate or remove radioactive waste that was abandoned. Timeline may be 4 to 6 weeks before Radiation Safety has staff resources to perform this operation and laboratory must remain locked, posted and in the department's possession during that time.
EHS | Universal waste and regulated equipment removed, assuming adequate warning has been provided (4 to 6 weeks), otherwise EHS will assist department in hiring an approved outside vendor to remove equipment at department's expense.
BM | Did the space have any special modifications due to the lab research activities? If so this modification needs to be returned to the pre-assignment condition including making repairs to ceilings, walls, and floors as required. Space should be in a condition that would require only minor patch, prep and paint to refresh the space
PI/LC | Copy of Signed (by PI and BM) Laboratory Safety Status form sent to EHS, ehs@wustl.edu or fax at 314-362-1995.
BM/PI/LC | Final walkthrough to determine lab is “broom clean” and ready for EHS inspection and decommissioning
PI/LC | EHS Biological & Chemical Safety auditor notified 2 weeks in advance that lab areas are ready for inspection. When cleared by EHS for decommissioning, their staff removes biohazard and chemical hazard symbols
PI/LC | Radiation Safety inspector notified 2 weeks in advance that lab areas are ready for survey and inspection. When cleared for decommissioning, EHS Radiation Safety inspector removes radioactive material symbols
BM | Puts in work order for custodial for final cleaning of the labs – billable request
EHS | All necessary signatures obtained on Laboratory Safety Status form
FMD/BM | FMD to walk-thru the lab with BM to confirm space is ready to be turned over
FMD | Makes recommendation to AVC of Research/EF Space Committee on Space Return, Acceptance or Denial
FMD | AVC Approves Request (assumes) and department is notified and physical planning updates inventory records
FMD | Change cores to allow lock-down of space
FMD | Add space to Space Bank in OSIS, updates available space records
This checklist applies to the following Rooms:
BM | Signature | Date | signed off By:
EHS | Signature | Date | signed off By:
FMD | Signature | Date | signed off By:
Attach a PDF of the floor plan with the rooms listed above indicated.