## Owner Provided Services Matrix
Owner Provided Services Responsibility Matrix
Activity | Project Manager | Move Coordinator | Design Team | Resource Mgmt Furniture & Design | Manager, Real Estate | Department |  |  | Comments
Furniture - Design, Procurement, Relocation or Installation
Determine if existing furniture is intended to be moved, new furniture to be purchased, and/or if existing furniture will need to be discarded - this should be accounted for in the project budget. | X
Design documents to be completed based on reuse of furniture or purchase of new. |  |  | X
If existing furniture is to be moved, a furniture inventory should be completed to determine if additional components will need to be purchased to meet new layout. |  |  |  | X
If new furniture components are required, a bid package should be created for procurement. Bids to be solicited, evaluated, and recommendation of vendor given to PM. |  |  |  | X
For new furniture or recovering of existing furniture, colors and fabrics should be coordinated with the interior finishes and preferences of the end users. |  |  |  | X
Furniture drawings should be developed based on specific systems of vendor selected during procurement. |  |  |  | X
Confirm furniture layouts and systems have been coordinated with architectural and MEP drawings - wall blocking requirements, power and data locations, etc. | X |  | X | X
Solicit bids for disassembling, relocating, and reinstalling existing furniture. |  | X* |  | X |  |  |  |  | Move Coordinator to verify what is part of Resource Management scope and only address items outside of their scope.
Establish the furniture installation date and include in overall project schedule. | X |  |  | X
Coordinate furniture installation with contractor/trades and the furniture installer, including working hours. | X |  |  | X
Coordinate building access, paths of travel, and elevator access for furniture delivery and/or relocation |  | X* |  | X |  |  |  |  | Move Coordinator to verify what is part of Resource Management scope and only address items outside of their scope.
Monitor furniture installation progress and provide updates to the PM. |  | X |  | X
Ensure that all furniture packing materials and temporary protection is removed/disposed of by furniture vendor. |  | X |  | X
Schedule a date with the furniture vendor and the customer for furniture punchlist. Obtain dates for completion and track accordingly. Communicate progress of completion with the customer and PM. |  | X* |  | X |  |  |  |  | Move Coordinator to verify what is part of Resource Management scope and only address items outside of their scope.
Notify PMs of any available furniture items that are in good condition for immediate use. |  | X
Solicit bids for disposal, dispose and/or remove any existing furniture as required in the vacated spaces. |  |  |  |  | X* | X* |  |  | The Manager, Real Estate will be involved in any leased spaces or spaces being returned back to the Dean. If the Department is backfilling its space, the Department is responsible for any disposal.
Activity | Project Manager | Move Coordinator | Design Team | Department |  |  |  |  | Comments
Equipment - Design, Procurement, Relocation or Installation of Lab/Clinical/Office Equipment
For laboratory or clinical projects, using the Lab Equipment Schedule, inventory all equipment - including size, power requirements, existing location, etc. Include specifications for any new equipment to be purchased for the project or in the future. Identify if equipment is being relocated or remaining. |  |  |  | X
For office projects or all other projects, use the simplified Equipment Schedule to inventory all equipment, such as appliances, copiers, fax, etc. - including size, power requirements, existing location, etc. Include specifications for any new equipment to be purchased for the project or in the future. Identify if equipment is being relocated or remaining. |  |  |  | X
Field survey all equipment identified to be relocated to complete any missing information from Equipment Schedules and to confirm that accurate information has been provided for incorporation into design. |  |  | X
Design documents to be completed based on Equipment Schedules. |  |  | X
Confirm equipment layouts have been coordinated with architectural and MEP drawings - wall blocking requirements, power and data locations, etc. | X
If pig tails are required to connect existing equipment to new outlets, coordinate procurement of pigtails with GC/Electrical Subcontractor. | X
Some laboratory equipment can be moved by standard moving companies, but many pieces of lab equipment will need specialty movers due to the proprietary disassembly/reassembly, calibration, service agreements or other sensitive components. The Department should determine which pieces of equipment require specialty movers and solicit the quotes for the move services. |  |  |  | X
Request approval of speciality move quotes from PM and request PO's to be issued by Accounting. |  | X
For speciality office equipment, like copiers or leased equipment, the Department should contact the leasing company for relocation services. |  |  |  | X
For all non-speciality equipment, develop RFP and solicit bids from moving vendors. |  | X
Evaluate moving bids and request approval from PM of selected move vendor. Request PO to be issued by Accounting. |  | X
Tag all equipment per designation provided on Equipment Schedule and Design Documents. |  |  |  | X
Verify and coordinate building access, paths of travel, and elevator access for furniture delivery and/or relocation. |  | X
Monitor equipment relocation and installation. |  | X
Ensure that all equipment packing materials and temporary protection is removed/disposed of by move vendor. |  | X
Purchase new movable equipment - solicitation of quotes, issuance of PO, management of delivery, certification, etc. |  |  |  | X
Dispose and/or remove any existing equipment as required in the vacated spaces. |  |  |  | X
Activity | Project Manager | Move Coordinator | Design Team | Resource Management | Custodial Services | General Contractor |  |  | Comments
Appliances, Custodial Accessories and Misc. Supplies/Equipment
Relocation of existing appliances to follow applicable equipment move procedure above.
If a project is purchasing appliances such as refrigerators, microwaves, ice makers, water dispensers, custodial dispensers, vending machines,etc. the PM should provide the plans showing the locations and provide specifications to the Move Coordinator for procurement. | X
Move Coordinator is responsible for procurement of appliances and requesting PO's from Accounting. |  | X
Schedule the delivery, receiving, uncrating, and installation of appliaces. |  | X
Procurement of vending machines as required. |  |  |  | X
Coordinate delivery and installation of vending machines. Coordination of product mix with end users/departments. |  | X
The Move Coordinator should review the plans and determine the number of kitchen/break area/lactation room/restroom/exam room dispensers required for the project PUBLIC AREAS (such as soap, paper towel, and toilet paper dispensers) to for delivery and installation. |  | X* | [6 empty] | Custodial Services will provide dispensers for public areas only. Any paper towel or soap dispensers in labs or non-common areas should be furnished and installed by the project and strock and maintained by the Department.
Custodial Services will order/furnish the required dispensers for installation in public areas. |  |  |  |  | X
The design should include elevations and locations for all Owner Furnished, Contractor installed items, especially for clinical areas. The Design Team should request cut sheets for all wall mounted items for coordination of backing and ADA accessibility. |  |  | X
Resource Management and the Department contact should complete the listing of equipment and furnishings to be purchased through the project - this is for fixed equipment to be OFCI. |  |  |  | X
PO's for fixed equipment should be requested from Accounting. | X
For projects requiring trash or recycle bins, the Move Coordiantor is responsible for procurement, requesting PO's from accounting, managing delivery and installation. |  | X
The General Contractor will install items noted as OFCI in the plans. | [5 empty] | X
Activity | Project Manager | Move Coordinator | TFC | WUSM IT | Low Voltage Subcontractor |  |  |  | Comments
Voice and Data - Activation and Installation
Provide the plans and specifications to the appropriate representatives from TFC/WUSM IT, identifying all voice data, fax and credit card machine lines. | X
Provide the Departmental Contacts to the appropriate representatives from TFC/WUSM IT. | X
Provide a project schedule, including substantial completion and move dates, to the appropriate representatives from TFC/WUSM IT. | X
Coordinate locations for data ports to be activated with Departmental Contacts. |  |  |  | X
Prepare As-Builts for low voltage indicating the port number for each location and deliver to TFC/WUSM IT prior to activation. |  |  |  |  | X
Activate data ports, complete cross connects in network closet. |  |  |  | X
Provide patch cables at activated data ports. |  |  |  | X
Coordinate with Departmental Contacts which phone numbers need to be relocated. Determine the date with the users when the new phones will become active and when the lines will switch from the prior location. It is possible in some cases to have the phones active in both locations for a short time during the move transition. |  |  | X
Install all phones. |  |  | X
Confirm all data ports are active, patch cables installed, and phones installed prior to move in. |  |  | X | X
Remove any phones remaining in vacated spaces as required. |  |  | X
Activity | Project Manager | Move Coordinator | Design Team | BJC Sign Shop | General Contractor | Department | Manager, Real Estate |  | Comments
Signage - Procurement and Installation
The PM should provide the plans and specifications to the appropriate representatives from BJC Sign Shop and Move Coordinator. | X
The PM should provide the Departmental Contacts to the appropriate representatives from BJC Sign Shop and Move Coordinator. | X
The PM should provide a project schedule, including substantial completion and move dates, to the appropriate representatives from BJC Sign Shop and Move Coordinator. | X
Coordinate locations for interior and exterior signage. |  |  | X | X
Compile signage schedule after locations have been coordinated, including sign types and sizes. |  |  |  | X
Confirm room numbers, room identification and/or room occupants to complete signage schedule with Departmental Contacts. |  | X |  | X
Confirm room numbers on with Space Management Coordinator to ensure tha numbering matches WUSM standards. |  | X
Review and approve finalized interior signage schedule prior to procurement/fabrication. | X |  |  |  |  | X
Procure and fabricate signage. |  |  |  | X
Establish the signage installation date and include in overall project schedule. | X
Coordinate furniture installation with contractor/trades, including working hours. | X
Monitor signage installation and confirm completion. Provide progress updates to PM. |  | X
Install signage. |  |  |  | X
Install any signage designated as OFCI. |  |  |  |  | X
If room signage is not complete at the time of move, temporary signage should be installed to assist with the move. |  | X
Coordinate removal of exterior signage form leased spaces. | [6 empty] | X
Activity | Project Manager | Move Coordinator | Design Team | Facilities Operations - Key Shop | Protective Services | Card Access Vendor | General Contractor | Best Lock Representative | Comments
Access Control - Keys & Cores, Card Access
During the design phase, coordinate locations of door locks and card readers with Departmental Contacts and Protective Services. | X |  | X
Determine if card readers will be on campus central system or stand alone. |  |  |  |  | X
Install rough-ins required for card readers per design documents. | [6 empty] | X
Furnish and install stand alone card readers. | [6 empty] | X
Obtain quote for campus central card access, request PO from accounting, coordinate procurement and installation of card readers. | X
Install and activate campus central card readers. | [5 empty] | X
Notify Protective Services of move dates or occupancy for activation of card access. | X
Coordinate badge activation and level of access with Departmental Contacts. |  |  |  |  | X
Keys & Cores For Large Projects
Facilities Operations with Protective Services will determine the appropriate keyway |  |  |  | X | X
Establish a work order for the project by emailing the Project Name, Project Number, and approximate installation date for the cores to the FISC. | X
The PM will meet with the customer and Best Lock representative and determine the Key and Core Schedule. | X
Best Lock representative will develop the Key and Core Schedule and send to the PM. | [7 empty] | X
The PM will have the customer approve and sign off on the Key and Core Schedule. The PM will give Best Lock representative the go-ahead to send the Key and Core codes to the WUSM Key shop via fax. | X
The project door hardware supplier will send the blank cores to Best Lock representative. | [6 empty] | X
Best Lock representative, with the Key and Core Schedule, will cut the keys and pin the cores for the project and will deliver the finished keys and cores to the FMD Supply Room | [7 empty] | X
The FMD Supply Room will notify the Key Shop when the keys and cores have arrived. The FO Key Shop will notify the PM that the keys and cores have arrived on campus. |  |  |  | X
Ten (10) working days in advance, the PM will notify the FO Key Shop and provide the Key and Core Schedule to install the cores. | X
The FO Key Shop will install the cores. |  |  |  | X
The PM will deliver the keys to the end user. | X
The General Contractor) for the project will provide construction cores when needed. | [6 empty] | X
Keys & Cores For Renovation Projects
Facilities Operations with Protective Services will determine the appropriate keyway |  |  |  | X | X
Establish a work order for the project by emailing the Project Name, Project Number, and approximate installation date for the cores to the FISC. | X
If reusing Cores – PM will contact FISC and request removal of cores for reuse. | X
FO Key Shop will remove requested cores for future reuse. |  |  |  | X
If using construction cores – PM will contact FO Customer Service and request installation of construction cores, identifying the quantity of construction keys required. | X
FO Key Shop will install construction cores and provide PM the keys within 2 days of request. |  |  |  | X
The PM will meet with the customer and Best Lock representative and determine the Key and Core Schedule. | X
Best Lock representative will develop the Key and Core Schedule and send to the PM. | [7 empty] | X
The PM will have the customer approve and sign off on the Key and Core Schedule. The PM will give Best Lock representative the go-ahead to send the Key and Core codes to the WUSM Key shop via fax. | X
The project door hardware supplier will send the blank cores to Best Lock representative. | [6 empty] | X
Best Lock representative, with the Key and Core Schedule, will cut the keys and pin the cores for the project and will deliver the finished keys and cores to the FMD Supply Room | [7 empty] | X
The FMD Supply Room will notify the Key Shop when the keys and cores have arrived. The FO Key Shop will notify the PM that the keys and cores have arrived on campus. |  |  |  | X
Ten (10) working days in advance, the PM will notify the FO Key Shop and provide the Key and Core Schedule to install the cores. | X
The FO Key Shop will remove the construction cores and install the new or reused cores on the requested date. |  |  |  | X
The PM will deliver the keys to the end user and collect any issued keys from the General Contractor. | X
Activity | Project Manager | Move Coordinator | Design Team | WUSM A/V | Audio Visual Vendor | General Contractor |  |  | Comments
Audio Visual Services
During the design phase, identify the locations and department requests for audio visual equipment. | X |  | X
Provide the plans and departmen contacts to the WUSM A/V representatives for review. | X
Develop bidding specifications for the A/V package based on current WUSM Standards. |  |  |  | X
Develop RFP including bid specifications and design drawings, solicit bids for A/V vendor (equipment and installation). Review bids and make recommendation to WUSM A/V for approval. | X
Approve selected vendor, including proposed equipment. |  |  |  | X
Provide a project schedule, including substantial completion and move dates, to the appropriate representatives from WUSM A/V and the Audio Visual Vendor.
Submit Audio Visual equipment rough-in drawings and equipment specifications for approval. |  |  |  |  | X
Install rough-ins required for audio visual equipment per design drawings and audio visual vendor submittals. | [5 empty] | X
Coordinate A/V equipment installation with contractor/trades and the A/V Vendor, including working hours. | X
Furnish and install audio visual equipment. |  |  |  |  | X
Monitor installation of A/V equipment and notify WUSM A/V of installation. | X
Activate and test all A/V equipment prior to occupancy. |  |  |  | X
Provide training to End Users on use of A/V equipment - function and features. |  |  |  | X | X
Activity | Project Manager | Move Coordinator | Move Vendor | Manager, Real Estate | Custodial Services | Facilities Engineering | Department |  | Comments
Move Services - Coordination of Schedule, Vendor, and Physical Move
The PM should provide the plans and specifications to the Move Coordinator. | X
The PM should provide any lab equipment, speciality equipment, or general equipment lists to the Move Coordinaror. | X
The PM should provide the Departmental Contacts to the Move Coordinator. | X
The PM should provide a project schedule, including substantial completion and move dates, to the Move Coordinator. | X
The Move Coordinator should review the scheduled timeframe for moves and notify the PM of any conflicts. |  | X
Schedule move planning kick off meeting with the PM, Departmental Contacts, and Move COordinator and walk the space to confirm the extent of the move. |  | X
Confirm all items to move are in the customer's current location or if there are additional items to move - items in storage or not visible, equipment that is arriving from another vendor, etc. |  | X
Confirm with Department if any key board trays, wall mounted items, etc. need to be removed and reinstalled. |  | X
Coordination moving dates and phasing with the Department within the scheduled move timeframe. |  | X
Develop RFP for moving services. |  | X
Conduct pre-bid walk through with moving vendors. |  | X
Solicit moving bids, evaluate bids, recommend selected move contractor to the PM. |  | X
Approve selected move vendor. | X
Request PO from accounting for move vendor. |  | X
Confirm all specialty equipment move proposals have been obtained by the Departmental Contacts and PO's have been issued. |  | X
Verfity Certificate of Insurance for move vendor lists WUSM and any additional building owners in the case of a lease. |  | X
Walk the path of travel for the move vendor, determine any issues and provide solutions. |  | X
Verify with adjacent departments that there are no major events that may conflict with the move and provide notification of potential noise and elevator usage. |  | X
Schedule move coordination meeting with Move Vendor, PM, Move Coordinator, TFC, IT, EH&S, etc. to discuss time requirements, schedule, delivery of packing materials, pre-move training dates, dept sequencing, building sequencing, telephone/data services, security, hazardous materials, future meetings and other items. |  | X
Conduct interim move planning meetings as required. |  | X
Schedule date for boxes, labels, and packing materials to be delivered to Department. |  | X
Provide training on proper packing methods/labeling procedures. |  | X
Deliver boxes and packing materials to Department. |  |  | X
Pack all items to be moved - including but not limited to office contents, lab contents, clinical content, computers, etc. according to the move and packing guidelines. | [6 empty] | X
Unpack file cabinets to boxes for move. | [6 empty] | X
Label all items that are moving: chairs, furniture, boxes, computers, keyboards, artwork, trash cans, etc. Confirm labels correctly identify the destination location.
Install temproary protection prior to move. |  |  | X
Confirm, prior to move, that temporary protection has been installed in elevators and corridors as required to protect building finishes. |  | X
Conduct a pre-move survey of existing conditions, noting any damage and taking pictures as necessary. |  | X
Inform Protective Services of the moving department, vendor, and schedule. |  | X
Verify that all items are packed before the move vendor arrives. |  | X
Verify all items are either locked or unlocked per instructions and keys are secure and accessible. | [6 empty] | X
Provide move vendor with any on campus traffic interuptions - other construction. |  | X
Prior to move, verify that all signage is installed in destination location. |  | X
Prior to move, notify Custodial Services of occupancy and start of regular service. |  | X
Stock public areas with paper towels, toilet paper, soap, and waste receptacles. |  |  |  |  | X* |  |  |  | For off campus or leased spaces, this is done by the Department or Property Manager.
Confirm that building systems are at set points for occupancy. | [5 empty] | X
On moving day, each Department to have a minimum of one contact person at the move location and one at destination location - provide names and contact information to Move Coordinator. | [6 empty] | X
Supervise and coordinate move vendor and installers on the job site during relocation. |  | X
Move all packed contents, equipment, furniture, etc. |  |  | X
Perform a final walk through to confirm all contents have been moved. |  | X | X |  |  |  | X
Nnotify PM that move is complete. |  | X
Coordinate with Department and or Leasing Agent on remaining items to turn over space: remove items as surplus, move to another department, Salvation Army, salvage, or trash. |  | X
Unpack items ASAP to meet the scheduled date of packing material pick up. Place all boxes, crates, packing materials in a single area after emptied. | [6 empty] | X
Schedule packing material pick ups. |  | X
Inform Move Coordinator of any damaged items. | [6 empty] | X
Confirm that all building finishes have been protected, record any damage as a result of the move and notify PM. |  | X
Contact Insurance Analyst regarding any Department items damaged during move. Confirm all claims resolved. |  | X
Confirm that the vacated areas are left "broom clean." |  | X |  | X |  |  |  |  | If the space is being returned to the Dean, the Manager, Real Estate will verify broom clean.
Complete Close Out Checklist including all referenced forms. | X
Signature
Signature
Signature
Signature

## w Move Services Vendor
Owner Provided Services Responsibility Matrix
Activity | Project Manager | Move Coordinator | Design Team | Resource Mgmt Furniture & Design | Manager, Real Estate | Department |  |  | Move Management Services Vendor | Comments
Furniture - Design, Procurement, Relocation or Installation
Determine if existing furniture is intended to be moved, new furniture to be purchased, and/or if existing furniture will need to be discarded - this should be accounted for in the project budget. | X
Design documents to be completed based on reuse of furniture or purchase of new. |  |  | X
If existing furniture is to be moved, a furniture inventory should be completed to determine if additional components will need to be purchased to meet new layout. |  |  |  | X
If new furniture components are required, a bid package should be created for procurement. Bids to be solicited, evaluated, and recommendation of vendor given to PM. |  |  |  | X
For new furniture or recovering of existing furniture, colors and fabrics should be coordinated with the interior finishes and preferences of the end users. |  |  |  | X
Furniture drawings should be developed based on specific systems of vendor selected during procurement. |  |  |  | X
Confirm furniture layouts and systems have been coordinated with architectural and MEP drawings - wall blocking requirements, power and data locations, etc. | X |  | X | X
Solicit bids for disassembling, relocating, and reinstalling existing furniture. |  |  |  | X |  |  |  |  | X* | Move Management Services Vendor to verify what is part of Resource Management scope and only address items outside of their scope.
Establish the furniture installation date and include in overall project schedule. | X |  |  | X
Coordinate furniture installation with contractor/trades and the furniture installer, including working hours. | X |  |  | X
Coordinate building access, paths of travel, and elevator access for furniture delivery and/or relocation |  |  |  | X |  |  |  |  | X* | Move Management Services Vendor to verify what is part of Resource Management scope and only address items outside of their scope.
Monitor furniture installation progress and provide updates to the PM. |  |  |  | X |  |  |  |  | X
Ensure that all furniture packing materials and temporary protection is removed/disposed of by furniture vendor. |  |  |  | X |  |  |  |  | X
Schedule a date with the furniture vendor and the customer for furniture punchlist. Obtain dates for completion and track accordingly. Communicate progress of completion with the customer and PM. |  |  |  | X |  |  |  |  | X* | Move Management Services Vendor to verify what is part of Resource Management scope and only address items outside of their scope.
Notify PMs of any available furniture items that are in good condition for immediate use. |  | X
Solicit bids for disposal, dispose and/or remove any existing furniture as required in the vacated spaces. |  |  |  |  | X* | X* |  |  |  | The Manager, Real Estate will be involved in any leased spaces or spaces being returned back to the Dean. If the Department is backfilling its space, the Department is responsible for any disposal.
Activity | Project Manager | Move Coordinator | Design Team | Department |  |  |  |  | Move Management Services Vendor | Comments
Equipment - Design, Procurement, Relocation or Installation of Lab/Clinical/Office Equipment
For laboratory or clinical projects, using the Lab Equipment Schedule, inventory all equipment - including size, power requirements, existing location, etc. Include specifications for any new equipment to be purchased for the project or in the future. Identify if equipment is being relocated or remaining. |  |  |  | X
For office projects or all other projects, use the simplified Equipment Schedule to inventory all equipment, such as appliances, copiers, fax, etc. - including size, power requirements, existing location, etc. Include specifications for any new equipment to be purchased for the project or in the future. Identify if equipment is being relocated or remaining. |  |  |  | X
Field survey all equipment identified to be relocated to complete any missing information from Equipment Schedules and to confirm that accurate information has been provided for incorporation into design. |  |  | X
Design documents to be completed based on Equipment Schedules. |  |  | X
Confirm equipment layouts have been coordinated with architectural and MEP drawings - wall blocking requirements, power and data locations, etc. | X | [7 empty] | X
If pig tails are required to connect existing equipment to new outlets, coordinate procurement of pigtails with GC/Electrical Subcontractor. | X
Some laboratory equipment can be moved by standard moving companies, but many pieces of lab equipment will need specialty movers due to the proprietary disassembly/reassembly, calibration, service agreements or other sensitive components. The Department should determine which pieces of equipment require specialty movers and solicit the quotes for the move services. |  |  |  | X
Request approval of speciality move quotes from PM and request PO's to be issued by Accounting. | [8 empty] | X*
For speciality office equipment, like copiers or leased equipment, the Department should contact the leasing company for relocation services. |  |  |  | X
For all non-speciality equipment, develop RFP and solicit bids from moving vendors. | [8 empty] | X
Evaluate moving bids and request approval from PM of selected move vendor. Request PO to be issued by Accounting. | [8 empty] | X
Tag all equipment per designation provided on Equipment Schedule and Design Documents. |  |  |  | X
Verify and coordinate building access, paths of travel, and elevator access for furniture delivery and/or relocation. | [8 empty] | X
Monitor equipment relocation and installation. | [8 empty] | X
Ensure that all equipment packing materials and temporary protection is removed/disposed of by move vendor. | [8 empty] | X
Purchase new movable equipment - solicitation of quotes, issuance of PO, management of delivery, certification, etc. |  |  |  | X
Dispose and/or remove any existing equipment as required in the vacated spaces. |  |  |  | X
Activity | Project Manager | Move Coordinator | Design Team | Resource Management | Custodial Services | General Contractor |  |  | Move Management Services Vendor | Comments
Appliances, Custodial Accessories and Misc. Supplies/Equipment
Relocation of existing appliances to follow applicable equipment move procedure above.
If a project is purchasing appliances such as refrigerators, microwaves, ice makers, water dispensers, custodial dispensers, vending machines,etc. the PM should provide the plans showing the locations and provide specifications to the Move Coordinator for procurement. | X
Move Coordinator is responsible for procurement of appliances and requesting PO's from Accounting. |  | X
Schedule the delivery, receiving, uncrating, and installation of appliaces. |  | X
Procurement of vending machines as required. |  |  |  | X
Coordinate delivery and installation of vending machines. Coordination of product mix with end users/departments. |  | X
The Move Coordinator should review the plans and determine the number of kitchen/break area/lactation room/restroom/exam room dispensers required for the project PUBLIC AREAS (such as soap, paper towel, and toilet paper dispensers) to for delivery and installation. |  | X* | [7 empty] | Custodial Services will provide dispensers for public areas only. Any paper towel or soap dispensers in labs or non-common areas should be furnished and installed by the project and strock and maintained by the Department.
Custodial Services will order/furnish the required dispensers for installation in public areas. |  |  |  |  | X
The design should include elevations and locations for all Owner Furnished, Contractor installed items, especially for clinical areas. The Design Team should request cut sheets for all wall mounted items for coordination of backing and ADA accessibility. |  |  | X
Resource Management and the Department contact should complete the listing of equipment and furnishings to be purchased through the project - this is for fixed equipment to be OFCI. |  |  |  | X
PO's for fixed equipment should be requested from Accounting. | X
For projects requiring trash or recycle bins, the Move Coordiantor is responsible for procurement, requesting PO's from accounting, managing delivery and installation. |  | X
The General Contractor will install items noted as OFCI in the plans. | [5 empty] | X
Activity | Project Manager | Move Coordinator | TFC | WUSM IT | Low Voltage Subcontractor |  |  |  | Move Management Services Vendor | Comments
Voice and Data - Activation and Installation
Provide the plans and specifications to the appropriate representatives from TFC/WUSM IT, identifying all voice data, fax and credit card machine lines. | X
Provide the Departmental Contacts to the appropriate representatives from TFC/WUSM IT. | X
Provide a project schedule, including substantial completion and move dates, to the appropriate representatives from TFC/WUSM IT. | X
Coordinate locations for data ports to be activated with Departmental Contacts. |  |  |  | X
Prepare As-Builts for low voltage indicating the port number for each location and deliver to TFC/WUSM IT prior to activation. |  |  |  |  | X
Activate data ports, complete cross connects in network closet. |  |  |  | X
Provide patch cables at activated data ports. |  |  |  | X
Coordinate with Departmental Contacts which phone numbers need to be relocated. Determine the date with the users when the new phones will become active and when the lines will switch from the prior location. It is possible in some cases to have the phones active in both locations for a short time during the move transition. |  |  | X
Install all phones. |  |  | X
Confirm all data ports are active, patch cables installed, and phones installed prior to move in. |  |  | X | X
Remove any phones remaining in vacated spaces as required. |  |  | X
Activity | Project Manager | Move Coordinator | Design Team | BJC Sign Shop | General Contractor | Department | Manager, Real Estate |  | Move Management Services Vendor | Comments
Signage - Procurement and Installation
The PM should provide the plans and specifications to the appropriate representatives from BJC Sign Shop and Move Coordinator. | X
The PM should provide the Departmental Contacts to the appropriate representatives from BJC Sign Shop and Move Coordinator. | X
The PM should provide a project schedule, including substantial completion and move dates, to the appropriate representatives from BJC Sign Shop and Move Coordinator. | X
Coordinate locations for interior and exterior signage. |  |  | X | X
Compile signage schedule after locations have been coordinated, including sign types and sizes. |  |  |  | X
Confirm room numbers, room identification and/or room occupants to complete signage schedule with Departmental Contacts. |  | X |  | X
Confirm room numbers on with Space Management Coordinator to ensure tha numbering matches WUSM standards. |  | X
Review and approve finalized interior signage schedule prior to procurement/fabrication. | X |  |  |  |  | X
Procure and fabricate signage. |  |  |  | X
Establish the signage installation date and include in overall project schedule. | X
Coordinate furniture installation with contractor/trades, including working hours. | X
Monitor signage installation and confirm completion. Provide progress updates to PM. |  | X
Install signage. |  |  |  | X
Install any signage designated as OFCI. |  |  |  |  | X
If room signage is not complete at the time of move, temporary signage should be installed to assist with the move. |  | X
Coordinate removal of exterior signage form leased spaces. | [6 empty] | X
Activity | Project Manager | Move Coordinator | Design Team | Facilities Operations - Key Shop | Protective Services | Card Access Vendor | General Contractor | Best Lock Representative | Move Management Services Vendor | Comments
Access Control - Keys & Cores, Card Access
During the design phase, coordinate locations of door locks and card readers with Departmental Contacts and Protective Services. | X |  | X
Determine if card readers will be on campus central system or stand alone. |  |  |  |  | X
Install rough-ins required for card readers per design documents. | [6 empty] | X
Furnish and install stand alone card readers. | [6 empty] | X
Obtain quote for campus central card access, request PO from accounting, coordinate procurement and installation of card readers. | X
Install and activate campus central card readers. | [5 empty] | X
Notify Protective Services of move dates or occupancy for activation of card access. | X
Coordinate badge activation and level of access with Departmental Contacts. |  |  |  |  | X
Keys & Cores For Large Projects
Facilities Operations with Protective Services will determine the appropriate keyway |  |  |  | X | X
Establish a work order for the project by emailing the Project Name, Project Number, and approximate installation date for the cores to the FISC. | X
The PM will meet with the customer and Best Lock representative and determine the Key and Core Schedule. | X
Best Lock representative will develop the Key and Core Schedule and send to the PM. | [7 empty] | X
The PM will have the customer approve and sign off on the Key and Core Schedule. The PM will give Best Lock representative the go-ahead to send the Key and Core codes to the WUSM Key shop via fax. | X
The project door hardware supplier will send the blank cores to Best Lock representative. | [6 empty] | X
Best Lock representative, with the Key and Core Schedule, will cut the keys and pin the cores for the project and will deliver the finished keys and cores to the FMD Supply Room | [7 empty] | X
The FMD Supply Room will notify the Key Shop when the keys and cores have arrived. The FO Key Shop will notify the PM that the keys and cores have arrived on campus. |  |  |  | X
Ten (10) working days in advance, the PM will notify the FO Key Shop and provide the Key and Core Schedule to install the cores. | X
The FO Key Shop will install the cores. |  |  |  | X
The PM will deliver the keys to the end user. | X
The General Contractor) for the project will provide construction cores when needed. | [6 empty] | X
Keys & Cores For Renovation Projects
Facilities Operations with Protective Services will determine the appropriate keyway |  |  |  | X | X
Establish a work order for the project by emailing the Project Name, Project Number, and approximate installation date for the cores to the FISC. | X
If reusing Cores – PM will contact FISC and request removal of cores for reuse. | X
FO Key Shop will remove requested cores for future reuse. |  |  |  | X
If using construction cores – PM will contact FO Customer Service and request installation of construction cores, identifying the quantity of construction keys required. | X
FO Key Shop will install construction cores and provide PM the keys within 2 days of request. |  |  |  | X
The PM will meet with the customer and Best Lock representative and determine the Key and Core Schedule. | X
Best Lock representative will develop the Key and Core Schedule and send to the PM. | [7 empty] | X
The PM will have the customer approve and sign off on the Key and Core Schedule. The PM will give Best Lock representative the go-ahead to send the Key and Core codes to the WUSM Key shop via fax. | X
The project door hardware supplier will send the blank cores to Best Lock representative. | [6 empty] | X
Best Lock representative, with the Key and Core Schedule, will cut the keys and pin the cores for the project and will deliver the finished keys and cores to the FMD Supply Room | [7 empty] | X
The FMD Supply Room will notify the Key Shop when the keys and cores have arrived. The FO Key Shop will notify the PM that the keys and cores have arrived on campus. |  |  |  | X
Ten (10) working days in advance, the PM will notify the FO Key Shop and provide the Key and Core Schedule to install the cores. | X
The FO Key Shop will remove the construction cores and install the new or reused cores on the requested date. |  |  |  | X
The PM will deliver the keys to the end user and collect any issued keys from the General Contractor. | X
Activity | Project Manager | Move Coordinator | Design Team | WUSM A/V | Audio Visual Vendor | General Contractor |  |  | Move Management Services Vendor | Comments
Audio Visual Services
During the design phase, identify the locations and department requests for audio visual equipment. | X |  | X
Provide the plans and departmen contacts to the WUSM A/V representatives for review. | X
Develop bidding specifications for the A/V package based on current WUSM Standards. |  |  |  | X
Develop RFP including bid specifications and design drawings, solicit bids for A/V vendor (equipment and installation). Review bids and make recommendation to WUSM A/V for approval. | X
Approve selected vendor, including proposed equipment. |  |  |  | X
Provide a project schedule, including substantial completion and move dates, to the appropriate representatives from WUSM A/V and the Audio Visual Vendor.
Submit Audio Visual equipment rough-in drawings and equipment specifications for approval. |  |  |  |  | X
Install rough-ins required for audio visual equipment per design drawings and audio visual vendor submittals. | [5 empty] | X
Coordinate A/V equipment installation with contractor/trades and the A/V Vendor, including working hours. | X
Furnish and install audio visual equipment. |  |  |  |  | X
Monitor installation of A/V equipment and notify WUSM A/V of installation. | X
Activate and test all A/V equipment prior to occupancy. |  |  |  | X
Provide training to End Users on use of A/V equipment - function and features. |  |  |  | X | X
Activity | Project Manager | Move Coordinator | Move Vendor | Manager, Real Estate | Custodial Services | Facilities Engineering | Department |  | Move Management Services Vendor | Comments
Move Services - Coordination of Schedule, Vendor, and Physical Move
The PM should provide the plans and specifications to the Move Management Services Vendor. | X
The PM should provide any lab equipment, speciality equipment, or general equipment lists to the Move Management Services Vendor. | X
The PM should provide the Departmental Contacts to the Move Management Services Vendor | X
The PM should provide a project schedule, including substantial completion and move dates, to the Move Management Services Vendor. | X
The Move Management Services Vendor should review the scheduled timeframe for moves and notify the PM of any conflicts. | [8 empty] | X
Schedule move planning kick off meeting with the PM, and Departmental Contacts and walk the space to confirm the extent of the move. | [8 empty] | X
Confirm all items to move are in the customer's current location or if there are additional items to move - items in storage or not visible, equipment that is arriving from another vendor, etc. | [8 empty] | X
Confirm with Department if any key board trays, wall mounted items, etc. need to be removed and reinstalled. | [8 empty] | X
Coordination moving dates and phasing with the Department within the scheduled move timeframe. | [8 empty] | X
Develop RFP for moving services. | [8 empty] | X
Conduct pre-bid walk through with moving vendors. | [8 empty] | X
Solicit moving bids, evaluate bids, recommend selected move contractor to the PM. | [8 empty] | X
Approve selected move vendor. | X
Request PO from accounting for move vendor. | X
Confirm all specialty equipment move proposals have been obtained by the Departmental Contacts and PO's have been issued. | [8 empty] | X
Verfity Certificate of Insurance for move vendor lists WUSM and any additional building owners in the case of a lease. | X
Walk the path of travel for the move vendor, determine any issues and provide solutions. | [8 empty] | X
Verify with adjacent departments that there are no major events that may conflict with the move and provide notification of potential noise and elevator usage. | X
Schedule move coordination meeting with Move Vendor, PM, TFC, IT, EH&S, etc. to discuss time requirements, schedule, delivery of packing materials, pre-move training dates, dept sequencing, building sequencing, telephone/data services, security, hazardous materials, future meetings and other items. | [8 empty] | X
Conduct interim move planning meetings, schedules and update reports as required. | [8 empty] | X
Schedule date for boxes, labels, and packing materials to be delivered to Department. | [8 empty] | X
Provide training on proper packing methods/labeling procedures. | [8 empty] | X
Deliver boxes and packing materials to Department. |  |  | X
Pack all items to be moved - including but not limited to office contents, lab contents, clinical content, computers, etc. according to the move and packing guidelines. | [6 empty] | X
Unpack file cabinets to boxes for move. | [6 empty] | X
Label all items that are moving: chairs, furniture, boxes, computers, keyboards, artwork, trash cans, etc. Confirm labels correctly identify the destination location.
Install temproary protection prior to move. |  |  | X
Confirm, prior to move, that temporary protection has been installed in elevators and corridors as required to protect building finishes. | [8 empty] | X
Conduct a pre-move survey of existing conditions, noting any damage and taking pictures as necessary. | [8 empty] | X
Inform Protective Services of the moving department, vendor, and schedule. | X
Verify that all items are packed before the move vendor arrives. | [8 empty] | X
Verify all items are either locked or unlocked per instructions and keys are secure and accessible. | [6 empty] | X
Provide move vendor with any on campus traffic interuptions - other construction. | X
Prior to move, verify that all signage is installed in destination location. | X
Prior to move, notify Custodial Services of occupancy and start of regular service. | X
Stock public areas with paper towels, toilet paper, soap, and waste receptacles. |  |  |  |  | X* |  |  |  |  | For off campus or leased spaces, this is done by the Department or Property Manager.
Confirm that building systems are at set points for occupancy. | [5 empty] | X
On moving day, each Department to have a minimum of one contact person at the move location and one at destination location - provide names and contact information to Move Coordinator. | [6 empty] | X
Supervise and coordinate move vendor and installers on the job site during relocation. | [8 empty] | X
Move all packed contents, equipment, furniture, etc. |  |  | X
Perform a final walk through to confirm all contents have been moved. |  |  | X |  |  |  | X |  | X
Nnotify PM that move is complete. | [8 empty] | X
Coordinate with Department and or Leasing Agent on remaining items to turn over space: remove items as surplus, move to another department, Salvation Army, salvage, or trash. | X
Unpack items ASAP to meet the scheduled date of packing material pick up. Place all boxes, crates, packing materials in a single area after emptied. | [6 empty] | X
Schedule packing material pick ups. | [8 empty] | X
Inform Move Services Vendor of any damaged items. | [6 empty] | X
Confirm that all building finishes have been protected, record any damage as a result of the move and notify PM. | [8 empty] | X
Contact Insurance Analyst regarding any Department items damaged during move. Confirm all claims resolved. | X
Confirm that the vacated areas are left "broom clean." |  |  |  | X |  |  |  |  | X | If the space is being returned to the Dean, the Manager, Real Estate will verify broom clean.
Complete Close Out Checklist including all referenced forms. | X
Signature
Signature
Signature
Signature