## Slide 1
Project Delivery
Business Operations Detailed
June 2015

## Slide 2: Step 1: Needs Development
Step 1: Needs Development (Jennifer)
Obtain Project number from Construction Management System
The Construction Management System auto generates the number. When the project request is received a decision is made within facilities to start the review as a initiative.
- In this step it is critical to enter all known information into the Construction Management System. This includes but isn’t limited to: Building, Floor, room(s), Department, Proposed use, Scope of Work.

## Slide 3: Step 2: Scope Development
Step 2: Scope Development (Janice)
  Create Resolution
  Narrative Document highlighting scope of work , cost and funding sources. This document’s primary focus provide information to the various approval committees.
  Present Resolution at various approval committees depending on financial threshold of project
  For some committees the resolution plus a presentation is used to obtain approval.

## Slide 4: The Business Operations
Approval Levels
Less than $100K
Asst. V.C. - Facilities
Capital Planning - Monthly Review
$100K - $499,999
Executive Vice Chancellor
Capital Planning - Monthly Review
Projects Committee -Monthly Review
$500K - $1,999,999
Capital Planning
Executive Vice Chancellor
Projects Committee (Chancellor approval)
Med. Finance Committee ($1 Million & above)
$2M - $4,999,999
Capital Planning
Executive Vice Chancellor
Projects Committee (Chancellor approval)
Med. Finance Committee
B & G Committee
$5M and above
Capital Planning
Executive Vice Chancellor
Projects Committee (Chancellor approval)
Med. Finance Committee
B & G Committee
Executive Committee

## Slide 5: Step 2: Scope Development
Step 2: Scope Development (Janice)
  After all approvals are obtained, set up funds in the financial system and the CMS (Construction Management System).
    Depending on size of project, this could be Property Accounting or Business Operations. The funds are set up via journal or budget adjustment in AIS.
    In CMS the committee approvals will be recorded and will generate the project budget.

## Slide 6: Step 2: Scope Development
  Notify stakeholders when funds are available in financial system via email from Business Operations
  Create work request in Work Order System
    Once an initiative becomes a project, it should be set up in the Work Order System
    This allows Facilities to bill out services

## Slide 7: Step 3: Selection of Design Team
Step 3: Selection of Design Team (Angie)
Prepare contract agreement
  PM submits contract checklist and/or proposal to Business Operations
  The required information is entered into the contract template in CMS
  Business Operations generates, saves , and sends the contract to the PM for review and approval through the CMS workflow
Send contract electronically to A/E for signature
  After A/E signs, contract is routed through the CMS workflow for University approval

## Slide 8: Step 3: Selection of Design Team
Create purchase order in financial system
  The PO is created by Business Operations in Marketplace which feeds AIS and will feed the CMS the details

## Slide 9: Step 4: Design Phase
There are no Business Operations tasks in this step

## Slide 10: Step 5: Selection of Contractor
Step 5: Selection of Contractor (Jennifer)
Did we have 3 competitive bids?
  Some projects require a specific contractor for a variety of reasons and are not competitively bid. In this instance sole source justification and approval is required
  If proposal exceeds $25k, the university purchasing policy requires three competitive bids.
  Reason why we might not competitively bid:
  Project requires expertise of a certain vendor
  Emergency repair/project (accelerated project timeline)
  Equipment repair requires use of a particular vendor

## Slide 11: Step 5: Selection of Contractor
Step 5: Selection of Contractor
  In the absence of the 3 competitive bids, a Supplier Selection Justification Form (Sole Source form) must be completed. The approval of the form depends upon the monetary amount
  Create PO or Standard form of agreement and obtain approvals

## Slide 12: Step 6: Construction Phase
Step 6: Construction Phase (Angie)
Review and process progress payments
Vendor e-mails Business Operations invoice
Review to validate: PO#, Contract amounts match proposals, prior payments, accuracy of amounts, relevant lien waivers, direct payments to MBE/WBE subcontractors
After review enter into the Construction Management System and route to PM & Fiscal Administrator for review/approval
Save the invoice electronically in the project file

## Slide 13: Step 6: Construction Phase
Step 6: Construction Phase
After all reviews/approvals, we make a Xerox copy of invoice and put in campus mail to CFU for payment processing. We keep copy and date stamp.
Monitor payment status. Once paid we can throw our paper copy away.

## Slide 14: Step 6: Construction Phase
Step 6: Construction Phase (Jennifer)
Process change orders as necessary
Reasons why a change order occurs (appropriate approvals must be obtained prior to the creation of the change order)
Scope change (PM manual has a complete list of reasons why scope might change – PCO Reason & Terms form)
Spending of contingencies

## Slide 15: Step 6: Construction Phase
Step 6: Construction Phase
PM sends Business Operations a request for a Change Order including the PCO reasons and term sheet form.
  Validate project has funding available
  If funding is not sufficient then getting additional funding requires going back to Step #2
Create change order in the Construction Management System and route for external approvals
After external approvals have been obtained Change Order is entered into AIS and routed for appropriate internal approvals.

## Slide 16: Step 7: Transition, Activation and Closeout
Step 7: Transition, Activation and Closeout (Janice)
Project Close Out File
  Review Encumbrances & remaining set asides
    - Looking for open encumbrances that have not been paid and reviewing the list with PM and or vendor.
  Close out project
  - Once all open encumbrances are eliminated and no additional POs are pending
    Project is marked complete in the Construction Management System.
    Account in AIS is closed and residual funding returned to original sources.

## Slide 17: Step 7: Transition, Activation and Closeout
Step 7: Transition, Activation and Closeout
Project Close Out File
  Review Post Project Evaluation feedback for process improvement opportunities.

## Slide 18: Wrap Up
Keys to Success:
Communication
Getting appropriate approvals
Reconciling invoices with purchase orders and/or contracts.
Follow through to make sure CFU pays invoices.

## Slide 19: Questions / Discussion