## Slide 1
Activation, Transition & Closeout – Step 7
June 2015

## Slide 2: Activation, Transition & Close Out
Step 1: Needs Development
Step 2: Scope Development
Step 3: Selection of Design Team
Step 4: Design Phase
Step 5: Selection of Contractor
Step 6: Construction Phase
Step 7: Activation, Transition and Close Out
Wrap-Up Summary & Q/A

## Slide 3: Step 7: Activation, Transition & Close Out
Activation and Transition
Closeout
Final Payments
& Project Closeout
Substantial Completion & Occupancy
Record Documents
Validate Final Deliverables
Customer Transition Plan

## Slide 4: Step 7: Activation, Transition & Close Out
Activation Activities Include:
Providing attic stock per the requirements of the specification
Ensuring a transitional and operational plan is in place with Facilities Operations and the Users
All fire, life and safety requirements have been met (Contractor to call for Building and Fire Inspections)
Building systems have been tested and commissioned
Building systems equipment training has been conducted
IT communication services have been established (Medical Networking Svcs and TFC)
Locks installed, keys delivered, access control initiated
Way-finding and Room ID signage installed
Furniture delivered and installed
Move Planning with User Groups
Project Reporting & Closeout Form

## Slide 5: Step 7: Activation, Transition & Close Out
Transition Meetings
Facilities Staff Training and Orientation - The Planner/PM is to schedule with the General Contractor training and orientation session(s) with the subcontractors or vendors of the new systems. This would include using the basis of design as a roadmap to train Facilities staff.
Department/Customer Training - In the event of new equipment installation by the Project Team, the Planner/PM will ensure the Contractor provides orientation and materials to the customer for their use in future maintenance of the equipment that will be their responsibility going forward.
Receipt and Acceptance of Contractor Test and Balance Report - Prior to project completion, discuss with the General Contractor and Test and Balance subcontractor (and Commissioning Agent, if applicable) the timing for receipt of the Test and Balance report. This report must be completed prior to occupancy and turned over to Facility Operations staff for use.

## Slide 6: Step 7: Activation, Transition & Close Out
Transition Meetings (cont.)
Planner/PM should discuss project timing custodial need with the Custodial Services Manager as well as provide a floor plan and any care instructions of the area for custodial service orientation. Align service needs with established service levels and time staffing assignments with occupancy dates. Determine access by keys or otherwise and make provisions as needed.
EH&S should be familiar with the project from previous project reviews but it is good to communicate date of occupancy and if planning a move, EH&S should be integral in the move planning and pre-move training. EH&S is to be involved with all laboratory moves. If the new space is a clinic, contact Infection Control (BJH or WUSM) for a final inspection.
If a project has Access Control requirements, provide Protective Services (protectiveservices@wusm.wustl.edu) with a list of names (provided by the department) to be entered into the access control program. Prior to the move, plan for orientation walk-throughs with the Department staff so they can become familiar with the new location and become familiar with all the new conditions.

## Slide 7: Step 7: Activation, Transition & Close Out
Final Commissioning – Test & Balance
The commissioning process is the verification of the performance of building systems and the training of Facilities Operations personnel. Systems to be commissioned vary according to project type but most typically involve the HVAC system.
Confirm Receipt of Test and Balance Report - If an independent Commissioning Agent (CxA) is involved, he/she will assist with obtaining and interpreting the Test and Balance (T&B) Report.
Final resolution of any outstanding commissioning items - The CxA will keep a log of items for resolution beginning early in the project. With the Planner/PM, the CxA will manage the log of outstanding commission items working with the General Contractor and MEP subcontractors along with the Facilities Maintenance staff to bring to full resolution.
Confirm Working Building Automation System (BAS) Graphics are loaded (visible in Facilities Computer Room) - This can often be the most difficult part of transition due to the nature of the way Controls Contractors approach their work. Completion of the working graphics is important so that the Facilities Maintenance staff can properly operate and maintain the building systems servicing the project area.

## Slide 8: Step 7: Activation, Transition & Close Out
Punch List Verification
At the end of projects and even during the Punch List stage, the Users will often request items to be added or changed from the Contract Documents. Sometimes additional costs are involved due to the change. Such changes needed to be tracked, written up for approval on the Department-Request for Change Form for approval prior to using project funds for such purposes unless it is a clear use of Contingency.
Additionally, items that are not in the Documents need to be added to meet required function, such as an additional light, or sign, or other such items. The Planner/PM is to use good judgment and seek approval, if uncertain, and track the changes for completion. As a reminder, the Planner/PM should track change orders throughout the life of the project. The Planner PM will be required to report on these at closeout of the project and it will be part of the project evaluation.

## Slide 9: Step 7: Activation, Transition & Close Out
Move Planning
Establish move time frame - Working with the Move Coordinator, the Planner/PM should establish the move time frame at the beginning of the project and show it on the construction schedule as a separate line item.
The move should be planned to have the least negative impact on the business operations but also must be balanced within the project means. The Planner/PM is to work with the customer and the entire team to determine the best approach. When the time frame is established, communicate to all involved and document on the project schedule.
Determine Items to be moved, purchased or discarded – Furniture, Equipment, Other Contents/Items and Coordination of Voice/Data Activations.

## Slide 10: Step 7: Activation, Transition & Close Out
Selection of Mover and Specialty Movers
Mover Bidding - The Planner/PM should work with the Move Coordinator in the selection of the mover for the project. Resource Management has several pre-qualified movers with standing agreements. Depending on the size of the move, bids will need to be received for moving services.
The Move Coordinator sets up a pre-move bidder walk-through to review all the areas and items to be moved. The Move Coordinator should provide movers with the time frame and phases of the move and floor plans of the areas being vacated and moved into.
After mover bids are received, careful review should take note of amount of move materials provided, protection for building finishes, number of man hours and days for the move and number of trucks used for the move. This assists with the detailed comparison and planning for the actual move.
Specialty Movers - Some laboratory equipment can be moved by furniture/contents movers but many pieces of lab equipment will need specialty movers due to the proprietary disassembly/reassembly by the vendor, calibration, service agreements or some other sensitive nature of the equipment. Biosafety cabinets and incubators are usually moved by a lab equipment mover due to the recertification and special preparation and setup required.

## Slide 11: Step 7: Activation, Transition & Close Out
Development of Move Plan/Detailed Move Schedule
The Planner/PM and the Move Coordinator should initiate move planning and customer transition meetings between the Project Team, Operations staff, building occupants, and other stakeholders prior to substantial completion (depending on the complexity of the project). It is important to begin early to allow adequate time to address issues or prepare agreements prior to building occupancy and turnover to Facilities Operations and other school departments. Meetings should continue on a regular basis until the project is complete and occupied. A follow up meeting should also be conducted just before the warranty expires (11 months after substantial completion).
All of the items/activities should be shown on a consolidated Move Planning Schedule to clearly document and establish expectations for all involved. Consider move timing with logistics and consider other contingencies while move planning, such as weather, other events on campus and other activities in origin or destination buildings.
Establish Move Date(s) - Schedule a meeting with all the necessary stakeholders to establish the exact move date(s). This will usually include the customer, the mover, the customer’s desktop support IT person, MSCITS, TFC, EHS (if a lab and/or lab support), Facilities Operations, Protective Services and potentially others depending on the move.
Keys/Access Control - Refer to the Core and Key Process for Large Projects and Core and Key Process for Renovation for process and contact information. Determine by the size of the project if the contractor or if Facilities Operations will install the cores.

## Slide 12: Step 7: Activation, Transition & Close Out
Development of Move Plan/Detailed Move Schedule (cont.)
Signage - The sign schedule will have been determined much earlier in the project. Room signs should be installed prior to the move to assist with room identification. If there is a delay in the delivery of signs, a temporary sign should be installed to assist with the move.
Appliances/Vending Machines - If a project is purchasing appliances, the Planner/PM should contact the Move Coordinator to work with the vendor for delivery date and location. Vending Machines are also coordinated with Resource Management for our approved vending supplier.
Furniture - The furniture installation date should be established early during the construction phase. Continue to coordinate with the furniture vendor and Resource Management Furniture and Design for status. Schedule a date with the furniture vendor and the customer for a furniture punch list determining any items that need repair correction, or completion. Communicate progress of completions with the customer.
Data Activations / Phone Installation - The Planner/PM should refer to the Phone Data Activation Guidelines. Exact data ports to be activated will have been determined earlier in the planning stages. The low voltage subcontractor is to prepare “as-builts” for low voltage indicating the port number for each location. This must be completed and delivered to MSCITS and TFC prior to activations. Begin this coordination during construction.

## Slide 13: Step 7: Activation, Transition & Close Out
Development of Move Plan/Detailed Move Schedule (cont.)
Audio Visual - Coordinate with the AV vendor dates they will have access to the space for installation and the duration necessary to complete their work. Allow for testing of the new system and in some cases, schedule a training session for the users with the AV vendor for familiarity in use of the new system.
Specialized Equipment - The Planner/PM should closely coordinate with the customer and EH&S as there may be several specialized pieces of equipment each with different vendors moving or installing. Coordinate with each to understand their needs and required time to complete their work. The Planner/PM should also walk the path of travel from where the piece of equipment will be unloaded to the project area to ensure there are no restrictions with regard to floor loading, overhead clearance and width of the path.
Biological, Chemical, Radiological Material - For lab moves, work with assigned EH&S staff to assess needs and to plan for move of biological, chemical or radiological materials. Each has special training and qualifications to handle.
Move Training - Most moves will go smoothly when thoroughly planned and involve the necessary stakeholders to the move. For lab moves, EH&S will conduct safety training to ensure compliance with safety practices and regulatory requirements for handling hazardous materials. The Move Coordinator is to schedule the move training meetings depending on project need and size. Damages - Damage occurring during the move should be addressed with the Insurance Analyst from General Property Insurance and the Move Coordinator.

## Slide 14: Step 7: Activation, Transition & Close Out
Post Move Follow Up
Condition of Vacated Space - It is expected that areas vacated by a move are to be left “broom clean”. Please refer to the Space Closure Checklist for further details and requirements.
Lab Decommissioning - If a lab is being vacated, please refer to the Lab Closure Checklist for further details and requirements.

## Slide 15: Step 7: Activation, Transition & Close Out
Record Documents
The Contractor, usually via the A/E, must deliver all O&M manuals to the Planner/PM for review prior to staff training on the equipment. The Planner/PM will work with the Contractor to schedule and manage the equipment start up and training. All building materials (also known as “attic stock”) must be delivered after the final punch list work is completed and accepted. Attic stock should be secured and managed by Facilities Operations.
The record documents are a record of formal change orders as well as modifications required to construct the facility. The contractor turns over the electronic copies of the record documents, including as built drawings to the A/E or Planner/PM as part of construction close out. The Planner/PM will then deliver them to the Space Information Coordinator using the Transmittal Form. The Planner/PM should complete the Space Utilization Update Form and deliver it to the Space Planner who will review for accuracy and approvals and forward to the Space Coordinator to update the Space Information System.
It is important that all Project Team members are familiar with FMD’s Records Management Guidelines, and the standard filing structure, to ensure consistency in the management of project files. The guidelines address both hard copy and electronic files. A complete project record is required and must be completed prior to administrative closeout.

## Slide 16: Step 7: Activation, Transition & Close Out
.
Final Endorsement & Occupancy
After final inspection and sign-off by the appropriate regulatory authorities, the Planner/PM will ensure all final inspections have been completed and approved.
The Planner/PM will complete a Project Occupancy Notification Form and place it in the Project Record with copies distributed to Space Information Planner, Senior Director of Facilities Operations and the Facilities Integrated Service Center Lead. Upon receipt of a Certificate of Substantial Completion, the Planner/PM submits to Business Operations to record and route for signature to the Director of Capital Projects. The facility or area may be occupied and the warranty period begins. This notification relays that the space has now been turned over to the customer and should be included in any applicable insurance policy for the University.
The warranty period is normally a one-year period after receipt of the Certificate of Substantial Completion. During this time, the goal is to provide consistent tracking and addressing of issues that occur during the warranty period. As issues arise after move-in, the Planner/PM will work with FMD in determining the responsible party. Contractor issues are immediately referred to the appropriate contractor for corrections and will be managed by the Planner/PM; design issues are referred to the A/E for disposition.
Warranty Reviews should be conducted by the Project Team after eleven months after occupancy for equipment and other building items. At the end of the warranty period, Facilities Operations will assume full control of the facility. Extended warranty items will continue to be addressed between the Planner/PM and FMD until the expiration of those warranties.

## Slide 17: Step 7: Activation, Transition & Close Out
Final Payments
After the A/E or Planner/PM confirms that the contractor has completed all punch list items they can recommend that the project be formally accepted by signing the Contractor’s final payment request.
Final payment requests (billing for 100% contract completion) are approved by the Planner/PM. Billing for release of retainage must be received separately
When prime does not self-perform all work, the Planner/PM will ensure a release of liens certificate is produced.

## Slide 18: Step 7: Activation, Transition & Close Out
Project Checklists
The A/E Contract Completion Checklist is completed by the Planner/PM and is required to be completed and submitted with the A/E’s final payment application. The Planner/PM is responsible for reviewing the checklist and verifying all items have been completed before approving the final payment.
The Project Delivery Checklist is a comprehensive checklist that can be used from the beginning of a project. The Planner/PM should conduct a final review of the Project Delivery Checklist to verify all project steps and tasks are complete.
The Project Closeout Checklist is required to be completed by the Planner/PM and Business Operations. The first section of the checklist is completed by the Planner/PM. All items must be completed before the project can be moved to “Administrative Close Out.”
The Planner/PM must confirm that all work deliverables have been completed and accepted. The Planner/PM must complete their section of the Project Closeout Checklist and the Director of Capital Projects or equivalent is ultimately responsible for verifying the completion of all required steps to move a project from Post Construction to Administrative Close Out.
Business Operations will complete their section of the Project Closeout Checklist. Once all items have been completed and Property Accounting has closed the project fund, the project status can be changed to “Closed.”

## Slide 19: Step 7: Activation, Transition & Close Out
Close Out Challenges
Claims: All claims must be resolved before final invoices can be approved
Complete deliverables: Final payments should not be approved if all deliverables are not complete or have not been received.
Professional Services payments: There are several things to verify before approving a final payment for professional services. In particular, the Planner/PM must verify with the Records Coordinator that the record documents have been received and are readable. Also, any remaining balances on the contract must be closed. Final payments should be marked “Final.”
Project billings: The Planner/PM is responsible for ensuring all project billing is received and closed out properly, including internal billing. Notice of Intent to Close Project will be utilized for this purpose. Any open encumbrances will be reduced by Business Operations.

## Slide 20: Step 7: Activation, Transition & Close Out
Questions / Discussion