## Project Close Out Checklist
Project Information
Project Number
Project Name
Planner / PM
Completed By | Close Out Item | Documents (if Applicable) - Project File Location | Status | Date Completed
Substanital Completion/Owner Occupancy
PM has completed and distributed the Project Occupancy Notification Form.
PM to confirm all building systems have been tested and commissioned and a operations plan is in place with Facilities Operations and the Users.
PM has completed punchlist walk through with A/E and has reviewed the punchlist for accuracy and completeness. If no A/E is contracted for CA, the PM shall document and distribute the punchlist directly to the Contractor.
For projects utilizing the services of an A/E, the Ai/E is responsible for issuing the Certificate of Substantial Completion. If no A/E is utilized, the PM is responsible for issuing the WUSM Certificate of Substantial Completion for the project. The punchlist should be attached to the certificate. The SC Certificate should be routed for signature by the A/E, Contractor and Director of Capital Projects. The final copy should be saved in the project file and distributed to Business Operations for record keeping.
PM has completed the Space Utilization Form and has delivered to the Space Coordinator for finalization of the Room Type.
PM has notified the Planning Analyst of lab renovation completion for updates to the lab quality rating.
PM to confirm that IT communication services have been established (Medical Networking Services and TFC).
PM/Move Coordinator to confirm that all signage, alliances and equipment is installed and that room numbers have been coordinated with Space Plannng.
PM to ensure that final keys and cores are in place and have been provided to the end user. PM has collected all building keys from contractor and contractor cores have been removed.
PM has confirmed that Final Cleaning is complete. If appropriate, final clean the space, wax floors, and fill restroom accessories.
PM has confirmed that all punchlist items have been completed (within 30 days of substantial completion for small projects).
PM has scheduled 1 year warranty walk through.
PM to confirm that all fire and life safety requirements have been met and that Contractor has received all final inspections and approval for occupancy from Building Inspector, Fire Marshall, Health Inspector, Others.
Copies of permits and any inspection documents to be saved in the project file. This includes Temporary Occupancy and Final Occupancy Permits.
| PM to coordinate with Facilities Operations/Business Operations regarding the start date of new occupancy, including the transfer of utility accounts. | See Utility Account Transfer Guidelines
PM to ensure that final keys and cores are in place and contractor cores have been removed.
PM to provide keys to end users.
PM has collected all building keys from the Contractor.
PM/Move Coordinator to confirm that all appliances and equipment have been delivered and installed.
PM/Move Coordinator to confirm that all signage is installed and that room numbers have been coordinated with Space Plannng.
PM to confirm that Audio Visual systems are installed and functional and that Users have been trained on operation.
Substanital Completion/Owner Occupancy- Vacated Space
PM/Move Coordinator has notifiied the Manger, Real Estate of vacated spaces returning to the Dean or leased space, who will complete the Returned Space forms.
If a lab is being vacated, the PM should notify the Planning Analyst of the vacation date. Planning Analyst to complete the Lab Closure Checklist.
WUSM Departmental Sign Off
EH&S has reviewed and approved applicable spaces.
Radiation Safety has reviewed and approved applicable spaces.
DCM has reviewed and approved applicable spaces.
Facilities Operations has reviewed and approved applicable spaces.
Custodial Services has reviewed and approved applicable spaces.
Protective Services has reviewed and approved all applicable spaces.
Post Occupancy/Project Closeout
PM has received, filed and distributed the Test, Adjust and Balance Report.
PM has received, filed and distributed the Final Commissioning Report.
PM has received, filed and distributed the Operations and Maintenance Manuals.
PM has received, filed and distributed the As Built and Record Documents. Ensure that the design team has incorporated red line drawings mark ups into final electronic drawing file.
PM has confirmed that all warranty documents are included in the O&M Manuals - including a listing of all products with warranties supplied on the project, highlighting products that carry an extended warranty.
PM to confirm that Facilities Operations and/or Users have received equipment training. Systems include but are not limited to Mechanical, Electrical, Plumbing, Fire Protection, Fire Alarm, Building Automation, Building Access, Lighting Controls, and A/V.
PM to confirm that all attic stock required by the specifications has been received and stored in an agreeable location with Facilities Operations.
PM has received, filed and distributed the Care Instructions for Building Materials.
PM has received, filed and distributed shop drawings and submittals as applicable.
PM has verified that all equipment has been installed and is operational after start up and/or move. Equipment specifications on file as required.
PM has verfied that all LEED documentation and close out tasks are complete if applicable.
PM has verified that all furniture has been installed and furniture punch list is complete. Furniture specifications and list on file as required.
PM to deliver the As-Built Documentation to the Space Information Coordinator.
PM has notified Property Insurance of project completion for transfer of insurance policies (for new construction only).
PM has verified copies of permits and any inspection documents to be saved in the project file. This includes Temporary Occupancy and Final Occupancy Permits.
PM has verfied that all LEED documentation and close out tasks are complete if applicable.
PM has completed the Professional Services Evaluation Form.
PM has completed the Construction Contractor Evaluation Form.
Administrative Coordinator has issued the Project Management and Project Delivery Customer Survey.
Financial Close Out
PM has confirmed that the contractor has completed all punch list items and delivered all record documents and will approve the final pay application.
PM has analyzed and closed all contract allowances if applicable.
PM has confirmed that all change orders have been issued to any contracts or purchase orders.
PM has issued change order to design team if appropriate. Often, the design team's final fee is calculated as a percentage of the final construction cost and must be adjusted when the final construction cost is determined.
Business Operations has confirmed that all encumbrances are closed. Ensure final payment amount balances with final contract amount or issue change orders as required to balance.
Business Operations has recovered escrow payments. (MSD, STLCO, STL City, Etc.)
Business Operations has confirmed that there are no outstanding tickets for internal charges open in Service Now.
PM/Business Operations has received all final MBE/WBE documentation.
PM has performed final liquidated damages analysis if applicable.
Business Operations has confirmed that all retention has been released.
PM/Business Operations has obtained the Consent of Surety to final payment if applicable.
Affidavit Monetary Obligations
Business Operations has confirmed that all Final Lien Waivers have been received.
WUSM Specific Close Out
| PM has completed the Space Utilization Form and has delivered to the Space Coordinator for finalization of the Room Type. | See Space Utilization Form
| PM has completed and distributed the Project Occupancy Notification Form. | See Project Occupancy Notification Form & Notice of Intent to Close Project
| Move Coordinator has completed the Move Checklist. | See Move Checklist
| PM/Move Coordinator has notified the Manager, Real Estate of vacated spaces returning to the Dean or leased space, who will complete the Returned Space forms. | See Returned Space Checklist
| If a lab is being vacated, the PM should notify the Planning Analyst of the vacation date. Planning Analyst to complete the Lab Closure Checklist. | See Lab Closure Checklist
PM has notified the Planning Analyst of lab renovation completion for updates to the lab quality rating.
Project Manager | Signature |  |  | Date
Business Operations | Signature |  |  | Date
Director of Capital Projects | Signature |  |  | Date
| Signature |  |  | Date